## Slide 1: Autonomous Quadrocopter Design Review
Brad Bergerhouse, Nelson Gaske, Austin Wenzel
Dr. Malinowski

## Slide 2: Outline
Original Goals
Abridged Project Description
Progress
Revised Goals
Current Schedule and Milestones

## Slide 3: Outline
Original Goals
Abridged Project Description
Progress
Revised Goals
Current Schedule and Milestones

## Slide 4: Original Goals
Implement backup fly-by-wire controls for safety and testing
Avoid obstacles using video and sensor feedback
Autonomously navigate through narrow passages using onboard sensors
Develop a quadrocopter platform for future senior projects

## Slide 5: Outline
Original Goals
Abridged Project Description
Progress
Revised Goals
Current Schedule and Milestones

## Slide 6: Functional Description
Interface BeagleBoard with XAircraft X650 Quadrocopter platform
Use BeagleBoard I/O to interface with sensors and remote controls
Develop passage following algorithm using minimal sensor input
Utilize image processing techniques for navigational purposes and goal criteria

## Slide 7: System Diagram

## Slide 8: Outline
Original Goals
Abridged Project Description
Progress
Revised Goals
Current Schedule and Milestones

## Slide 9: Progress
Platform Arrived. Assembly is complete, we are now working on a rotor guard solution
Close to having a working PWM solution
We have started on I2C
5V regulator is ready for installation
SUSAN corner detection on images in progress

## Slide 10: Completed Platform

## Slide 13: Quadrocopter Building

## Slide 14: Rotor Guards

## Slide 15
General DSP flowchart

## Slide 16: SUSAN corner detection

## Slide 17: Hindrances to Progress
BeagleBoard documentation (or lack there of)
Lack of standardized interfaces for major hardware components
Cross compiling kernel issues

## Slide 18: Attempts to output PWM to GPIO pins
Bash Script
C code
Servodrive kernel module
  Openembedded
  Bitbake

## Slide 19: Outline
Original Goals
Abridged Project Description
Progress
Revised Goals
Current Schedule and Milestones

## Slide 20: Revised Goals
Use sensors to avoid obstacles
Use camera to observe navigational marking and goal criteria
Fly-by-wire

## Slide 21: Outline
Original Goals
Abridged Project Description
Progress
Revised Goals
Current Schedule and Milestones

## Slide 22: Original Schedule
Chart: 
| Camera and Joystick Interfacing | Camera and DSP interfacing | Wireless and I2C Interfacing | Platform Assembly | PWM output design and testing | IR sensor Interfacing | Platform Power Testing | Communication Design | Navigation Design | Testing and Debugging | Presentation Preparation
Start Date | 40864 | 40878 | 40878 | 40927 | 40934 | 40941 | 40955 | 40934 | 40927 | 40993 | 41023
Days | 7 | 114 | 21 | 7 | 14 | 14 | 7 | 28 | 70 | 30 | 7

## Slide 23: Revised Schedule
Chart: 
| Camera and Joystick Interfacing | Camera and DSP interfacing | Wireless and I2C Interfacing | Platform Assembly | Platform Power Testing | PWM output design and testing | IR sensor Interfacing | Navigation Design | Testing and Debugging | Presentation Preparation
Start Date | 40864 | 40878 | 40940 | 40927 | 40934 | 40934 | 40954 | 40927 | 40993 | 41023
Days | 7 | 150 | 37 | 7 | 14 | 37 | 28 | 70 | 30 | 7
Start Date | 40864 | 40878 | 40940 | 40927 | 40934 | 40934 | 40954 | 40927 | 40993 | 41023
Days | 7 | 150 | 37 | 7 | 14 | 37 | 28 | 70 | 30 | 7

## Slide 24: Questions?