## project
Project Timeline
[6 empty] | Period: |  |  |  |  | 26
|  | Plan |  |  | Actual |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Task Name | Start Period | Duration | Actual Start | Actual Duration | Percent Complete | 2015-08-26 | 2015-08-30 | 2015-09-02 | 2015-09-06 | 2015-09-09 | 2015-09-13 | 2015-09-16 | 2015-09-20 | 2015-09-23 | 2015-09-27 | 2015-09-30 | 2015-10-04 | 2015-10-07 | 2015-10-11 | 2015-10-14 | 2015-10-18 | 2015-10-21 | 2015-10-25 | 2015-10-28 | 2015-11-01 | 2015-11-04 | 2015-11-08 | 2015-11-11 | 2015-11-15 | 2015-11-18 | 2015-11-22 | 2015-11-25 | 2015-11-29 | 2015-12-02 | 2015-12-06 | 2015-12-09 | 2015-12-13 | 2015-12-16 | 2015-12-20 | 2015-12-23 | 2015-12-27 | 2015-12-30 | 2015-01-03 | 2015-01-06 | 2015-01-10 | 2015-01-13 | 2015-01-17 | 2015-01-20 | 2015-01-24 | 2015-01-27 | 2015-01-31 | 2015-02-03 | 2015-02-07 | 2015-02-10 | 2015-02-14 | 2015-02-17 | 2015-02-21 | 2015-02-24 | 2015-02-28 | 2015-03-02 | 2015-03-06 | 2015-03-09 | 2015-03-13 | 2015-03-16 | 2015-03-20 | 2015-03-23 | 2015-03-27 | 2015-03-30 | 2015-04-03 | 2015-04-06 | 2015-04-10
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66
Team Coordination | 1 | 2 | 1 | 2 | 100%
Initial Simulink Modeling | 1 | 3 | 1 | 3 | 100%
Project Proposal Document | 3 | 10 | 3 | 10 | 100%
MATLAB Code Model based on initial Simulink Model | 4 | 2 | 4 | 2 | 100%
Cogging Torque Experimental and Research | 4 | 7 | 4 | 7 | 100%
Efficiency, Motor, Motor-Gen Load Curve | 4 | 2 | 4 | 2 | 100%
Team Coordination | 5 | 1 | 5 | 1 | 100%
Generator Simulink Model | 5 | 3 | 5 | 3 | 100%
Serial communication research and implementation | 5 | 5 | 5 | 5 | 100%
Theoretical Vehicle Prototype Design | 5 | 3 | 5 | 3 | 100%
Initial Controller Development | 7 | 3 | 7 | 3 | 0%
Rotary Encoder Resolution Algorithm | 7 | 4 | 7 | 4 | 100%
Rotary Encoder Model | 7 | 4 | 7 | 8 | 100%
Generator Experimental | 8 | 2 | 8 | 2 | 100%
Proposal Presentation | 8 | 4 | 8 | 4 | 100%
Team Coordination | 9 | 1 | 9 | 1 | 100%
Current Source Research and experimental | 9 | 7 | 9 | 18 | 100%
AtMega PWM Setup | 10 | 2 | 10 | 2 | 100%
Cogging Torque Model | 11 | 7 | 11 | 12 | 100%
Command Conditioning Simulink | 11 | 1 | 14 | 1 | 100%
H-Bridge Model | 12 | 2 | 16 | 2 | 100%
Team Coordination | 13 | 1 | 13 | 1 | 100%
Input Command | 13 | 5 | 15 | 4 | 100%
PWM Model | 14 | 7 | 15 | 3 | 100%
Experimental Thermal Measurements | 15 | 2 | 21 | 7 | 80%
Web Page Development/Updates | 15 | 5 | 15 | 5 | 100%
Team Coordination | 17 | 1 | 17 | 1 | 100%
PWM Frequency Optimized | 17 | 3 | 21 | 1 | 100%
Digital Filter | 17 | 4 | 17 | 4 | 0%
Disturbance Command | 18 | 4 | 17 | 4 | 100%
Kinematic Model | 18 | 4 | 17 | 4 | 100%
Progress Report Presentation 1 | 20 | 4 | 20 | 4 | 75%
Thermal Simulink Model | 20 | 4 | 22 | 5 | 80%
Team Coordination | 21 | 1 | 21 | 1 | 100%
I^2C and new D/As | 22 | 4 | 21 | 6 | 100%
Dynamic Model | 22 | 6 | 20 | 6 | 100%
Performance Review Document | 23 | 1 | 23 | 1 | 100%
Experimental Platform Integration | 24 | 9 | 24 | 9 | 40%
Team Coordination | 25 | 1 | 25 | 1 | 100%
Efficiency Model | 27 | 4 | 27 | 4 | 0%
Simulink Integration | 28 | 8 | 25 | 8 | 30%
Team Coordination | 29 | 1 | 29 | 1 | 0%
Controller Development | 35 | 8 | 35 | 8 | 0%
Team Coordination | 37 | 1 | 37 | 1 | 0%
Controller Model | 39 | 8 | 39 | 8 | 0%
Team Coordination | 41 | 1 | 41 | 1 | 0%
Controller Code | 41 | 5 | 41 | 5 | 0%
Terrain Testing | 42 | 1 | 42 | 1 | 0%
Simulink GUI Control | 42 | 9 | 42 | 9 | 0%
Team Coordination | 45 | 1 | 45 | 1 | 0%
Progress Report Presentation 2 | 46 | 4 | 46 | 4 | 0%
Experimental Platform Testing | 47 | 8 | 47 | 8 | 0%
Simulink System Testing | 47 | 8 | 47 | 8 | 0%
Team Coordination | 49 | 1 | 49 | 1 | 0%
Experimental Platform and Simulink Integration | 52 | 5 | 52 | 5 | 0%
Team Coordination | 53 | 1 | 53 | 1 | 0%
Experimental Platform and Simulink Testing | 56 | 8 | 56 | 8 | 0%
Team Coordination | 57 | 1 | 57 | 1 | 0%
Demo Prep | 57 | 2 | 57 | 2 | 0%
Final Report | 60 | 5 | 60 | 5 | 0%
Team Coordination | 61 | 1 | 61 | 1 | 0%
Final Presentation | 62 | 4 | 62 | 4 | 0%
Poster Presentation | 64 | 3 | 64 | 3 | 0%
Team Coordination | 65 | 1 | 65 | 1 | 0%